## Sheet1
# | Tasks | Time | Risk 1-10 | % Complete
1 | Create an output method | 1.0Hrs | 2 | 50
2 | Create a user input method and data validation method | 2.0Hrs | 2 | 0
3 | Create a basic quadratic calculation method | 2.0Hrs | 3 | 50
4 | Settting up the SVN for the project | 1.0Hrs | 3 | 0
5 | Looking into Unit Testing for C | 1.0Hrs | 3 | 0