## Sheet1
# | Tasks | Risk | Time Estimate | Time Actual | % Complete | User | Code Review
1 | Research Chipset to use | 2 | 1.0Hrs | 1.0Hr | 100 | Marcel | X
2 | Research Temperature Sensor | 2 | 1.0Hrs | 0.08Hrs | 100 | Marcel | X
3 | Research Humidity Sensor | 2 | 1.0Hrs | 1.0Hrs | 100 | Marcel | X
4 | Acquire Specs from Client(Dr. Kapenga) | 10 | 1.0Hrs | 1.0Hrs | 0 | All | X
5 | Set up Git repo | 1 | 0.05Hrs | 0.05Hrs | 100 | Marcel | X
6 | Start looking into Laravell | 2 | 2.0Hrs | 0Hrs | 22 | All | X