## Sheet1
# | Tasks | Risk | Time Estimate | Time Actual | % Complete | User | Code Review
1 | Create an output method | 2 | 1.0Hrs | 0.08Hrs | 50 | Mike | X
2 | Create a user input method and data validation method | 2 | 2.0Hrs | 0Hrs | 0 | Mike | X
3 | Create a basic quadratic calculation method | 3 | 2.0Hrs | 0.03Hrs | 50 | Mike | X
4 | Settting up the SVN for the project | 3 | 1.0Hrs | 0Hrs | 0 | All | X
5 | Looking into Unit Testing for C | 3 | 1.0Hrs | 0Hrs | 0 | All | X